## Sheet1
Mobile App
Number | Type | Area | Issue | Comments | Image
1 | Cosmetic: IOS screen sizing | Screens that use a keybouard in IOS | In IOS, the Next button is hidden under keyboard for the following screens (Profile creation, Social Creation Details and Social email). user cannot get to it once they start filling out the fields. | Resize similar to Android | See Image 1
2 |  | Add Email to Social | The application does not recognize that an email has been added unless an action has been taken. Error message occurs
3 | Cosmetic | Sign-up | Capitalization for Text Fields- When inputting my first and last name the text field defaults to lower case for the first letter. | Capitalize the first letters in names
4 |  | Sign-up | Country List- When typing characters, the first letters of the country do not go to the top | Can the country list default to the beginning of the country when inputting characters | See Image 2
5 | Cosmetic | Sign-up | Error message does not say "capitalization needed" for password | Change error message to "passwords must be at least 8 characters and contain one alpha, numeric, special and capitalized characters"
6 |  | Various | Profile picture not showing in all spots
7 | Cosmetic | Email invite sent after Social created | The email invite needs a space after the host name in the first paragrapgh | Insert a space in the email after the name | See Image 3
8 | Cosmetic | 5 slide intro | "Exit" hard to see in the 5 slide into. | Make larger and surronded by font | See Image 4
|  | Social video creation | Sound not working for Social video
Widget
Number | Type | Area | Issue | Comments | Image
9 |  | Accepting Invite on Moblie | When we accept invitation on email-it goes to the widget and not the application or ability to download. The layout of the widget does not look right so direct away from that experience (Create button is off the right side of the screen and create button not working) | Moblie email invite so force to download the application on Apple or Google
10 | Cosmetic | My Invites | In "My Invites", the create button is to create a Social. We should send downlouad link to registered email. The create button on mobie creates an IseBreaker video
11 |  | My Invites and My Socials (if no video created) | When select "Create"… send an email with download instructions and show this messahe... "An email has been sent to your registered email address with download instructions for the IseBreaker application. Please download and log in from your mobile device to create your IseBreaker video for this invite" | Add pop-up
#REF! |  |  | Social that was created did not show until I went to archive and back to active | No refresh of social list
#REF! |  | Update PW | update password page doesn't work.. no message given...
#REF! |  | Social creation: Invites | TXT or CSV file did not send emails | Can we put a template or an instruction pop-up for how to fill out a txt or csv file?
#REF! |  | Sign-up | In Sign-up, "OTP" enabled | Mute the OTP functionality so similar to mobile experience
#REF! | Cosmetic | Sign-up | In Sign-up, phone number is required | Do not make required
1 | Cosmetic | Profile Picture | Adding a Profile Picture flow... "OK" and "No" for choices. | Change to "Save" and "Back"
2 | Cosmetic | Profile Picture | Adding a Profile Picture- Camera selection does not work. Just attachment of a picture | Remove Camera?
3 | Cosmetic | Social | No back button in instructions pop-up | Add "Back" button in the Instructions when ctreating a Social
4 | Cosmetic |  | In heading- Change "My Interest" to "My Interests" | Add an "s"
|  | Social | No limit on Social description
1 | Cosmetic | Social | When deleting a video, change error message from "Are you sure you want to delete this iseBreaker ?" to "Are you sure you want to delete?" | Change error message
Application does not sign out
Admin Portal
Number | Type | Area | Issue | Comments | Image
25 |  | Admin | Topic questions page- once page is edited, the screen doesn't return to list view page
26 |  | Admin | Play video link don't work in video report screen
27 |  | Admin | City list needs to be editable or need to upload it from backend